## Project Timeline
Satellite Antenna Tracking Project Schedule
|  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  |  | MAY
Deliverable/Task |  | Owner | Duration | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
Concept of Operations |  |  | 1 w
| Executive Summary | David S | 1 w
| Background: Orbital Motion, Satellite Systems, Web Apps | David S | 1 w
| Background: Orbital Motion, Satellite Systems, Web Apps | Lewis, Potts | 1 w
| Background: Orbital Motion, Satellite Systems, Web Apps | Potts | 1 w
| Background: All Sections | All | 1 w
Scoping/Prototyping |  |  | 3 w
| Decide data objects & relationships | Lewis | 1 w
| Decide what to store in model versus externally | Higgins, Lewis | 3 w
| Wireframe | Higgins, Lewis | 1 w
| External data source permissions | Lewis | 3 w
| Detailed wireframe | Sohn | 1 w
Basic Water Budget Tool |  |  | 5 w
| Formatting input data | Lewis | 1 w
| Script for calculating landscape area from coefficient table | Higgins | 4 w
| Script for calculating water budget | Higgins | 3 w
| Webpage development | Noble, Rose, Potts | 1 w
| Connect geocoder | Higgins | 1 w
| QC/Testing | Lewis, Higgins | 1 w
Advanced Water Budget Tool |  |  | 3 w
| Develop domains for user-input and geoprocessing |  | 1 w
| User-prompt for delineating sprinkler zone |  | 1 w
| Design dialog box for user-prompt |  | 2 w
| Script for calculating water budget based on zones |  | 3 w
| Design output budget display |  | 2 w
| Correctness test of outputs |  | 1 w
Writing/Presentation |  |  | 2 w
| Report writing | All | 2 w
| Data | Lewis | 1 w
| Methods | Higgins | 1 w
| Results | Potts | 1 w
| Conclusion | Rose, Noble | 1 w
| Final presentation | Sohn | 1 w
| Deliverables | All | 1 w
External dependency/PostPoned/Completed